## Project Plan
Project X: Automated Attendance System - Project Plan
Deadline: May 02, 2025 | [7 empty] | Start Date : March 04, 2025
Task ID | Task Name | Subtask ID | Subtask Name | Estimated Hours | Assigned To | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Comments
1 | Project Initiation |  |  |  |  | 2025-03-01 | 2025-03-07 | 2025-03-01 | 2025-03-07
|  | 1.1 | Define Project Scope | 4 hours | Kissy Candia | 2025-03-01 | 2025-03-02 | 2025-03-01 | 2025-03-02 | Done
|  | 1.2 | Identify Stakeholders | 4 hours | Francis Lloyd Catog | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | Done
|  | 1.3 | Create Project Charter | 12 hours | Bjorn Dimsey Gofredo | 2025-03-04 | 2025-03-05 | 2025-03-04 | 2025-03-05 | Done
|  | 1.4 | Kickoff Meeting | 2 hours | Team A | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | Done
|  | 1.5 | Finalize Project Plan | 8 hours | Kissy Candia | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | Done
2 | Requirements Analysis |  |  |  |  | 2025-03-08 | 2025-03-14 | 2025-03-08 | 2025-03-14
|  | 2.1 | Gather Requirements | 16 | Team A | 2025-03-08 | 2025-03-10 | 2025-03-08 | 2025-03-10 | Done
|  | 2.2 | Document Requirements | 12 | Kissy Candia | 2025-03-11 | 2025-03-12 | 2025-03-11 | 2025-03-12 | Done
|  | 2.3 | Requirements Review | 8 | Bjorn Dimsey Gofredo | 2025-03-13 | 2025-03-14 | 2025-03-13 | 2025-03-14 | Done
3 | Design Phase |  |  |  |  | 2025-03-15 | 2025-03-22 | 2025-03-15 | 2025-03-22
|  | 3.1 | Create High-Level Design | 20 | Kissy Candia | 2025-03-15 | 2025-03-17 | 2025-03-15 | 2025-03-17 | Done
|  | 3.2 | Design Review | 4 | Francis Lloyd Catog | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | Done
|  | 3.3 | Create Detailed Design | 40 | Bjorn Dimsey Gofredo | 2025-03-19 | 2025-03-21 | 2025-03-19 | 2025-03-21 | Done
|  | 3.4 | Finalize Design | 8 | Kissy Candia | 2025-03-22 | 2025-03-22 | 2025-03-22 | 2025-03-22 | Done
4 | Implementation |  |  |  |  | 2025-03-23 | 2025-04-03 | 2025-03-23 | 2025-04-03
|  | 4.1 | Phase 1 Implementation | 80 | Team A | 2025-04-04 | 2025-04-10 | 2025-04-04 | 2025-04-10 | Done
|  | 4.2 | Phase 2 Implementation | 80 | Team A | 2025-04-11 | 2025-04-12 | 2025-04-11 | 2025-04-12 | Done
|  | 4.3 | Implementation Review | 8 | Team A | 2025-04-13 | 2025-04-22 | 2025-04-13 | 2025-04-22 | In Prgress
5 | Testing |  |  |  |  | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-14
|  | 5.1 | Create Test Cases | 16 | Kissy Candia | 2025-04-15 | 2025-04-18 | 2025-04-15 | 2025-04-18 | Done
|  | 5.2 | Execute Test Cases | 24 | Francis Lloyd Catog | 2025-04-19 | 2025-04-22 | 2025-04-19 | 2025-04-22 | In Prgress
|  | 5.3 | Bug Fixes | 16 | Bjorn Dimsey Gofredo | 2025-04-23 | 2025-04-28 | 2025-04-23 | 2025-04-28 | Not Started
6 | Deployment |  |  |  |  | 2025-04-11 | 2025-04-17 | 2025-04-11 | 2025-04-17
|  | 6.1 | Create Deployment Plan | 8 | Team A | 2025-04-12 | 2025-04-18 | 2025-04-12 | 2025-04-18 | Not Started
|  | 6.2 | Deployment | 16 | Team A | 2025-04-13 | 2025-04-19 | 2025-04-13 | 2025-04-19 | Not Started
|  | 6.3 | Post-Deployment Review | 8 | Team A | 2025-04-14 | 2025-04-20 | 2025-04-14 | 2025-04-20 | Not Started
7 | Project Closure |  |  |  |  | 2025-04-15 | 2025-04-21 | 2025-04-15 | 2025-04-21
|  | 7.1 | Document Lessons Learned | 8 | Kissy Candia | 2025-05-01 | 2025-05-02 | 2025-05-01 | 2025-05-02 | Not Started
|  | 7.2 | Final Project Report | 16 | Francis Lloyd Catog | 2025-05-02 | 2025-05-03 | 2025-05-02 | 2025-05-03 | Not Started