## Project Plan
Project X: Automated Attendance System - Project Plan
Deadline: May 02, 2025 | [7 empty] | Start Date : March 04, 2025
Task ID | Task Name | Subtask ID | Subtask Name | Estimated Hours | Assigned To | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Comments
1 | Project Initiation |  |  |  |  | 2025-03-01 | 2025-03-07 | 2025-03-01 | 2025-03-07
|  | 1.1 | Define Project Scope | 4 hours | Kissy Candia | 2025-03-01 | 2025-03-02 | 2025-03-01 | 2025-03-02 | Done
|  | 1.2 | Identify Stakeholders | 4 hours | Francis Lloyd Catog | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | Done
|  | 1.3 | Create Project Charter | 12 hours | Bjorn Dimsey Gofredo | 2025-03-04 | 2025-03-05 | 2025-03-04 | 2025-03-05 | In Progress
|  | 1.4 | Kickoff Meeting | 2 hours | Team A | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | Done
|  | 1.5 | Finalize Project Plan | 8 hours | Kissy Candia | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | In Progress
2 | Requirements Analysis |  |  |  |  | 2025-03-08 | 2025-03-14 | 2025-03-08 | 2025-03-14
|  | 2.1 | Gather Requirements | 16 | Team A | 2025-03-08 | 2025-03-10 | 2025-03-08 | 2025-03-10 | In Progress
|  | 2.2 | Document Requirements | 12 | Kissy Candia | 2025-03-11 | 2025-03-12 | 2025-03-11 | 2025-03-12 | In Progress
|  | 2.3 | Requirements Review | 8 | Bjorn Dimsey Gofredo | 2025-03-13 | 2025-03-14 | 2025-03-13 | 2025-03-14 | Pending
3 | Design Phase |  |  |  |  | 2025-03-15 | 2025-03-22 | 2025-03-15 | 2025-03-22
|  | 3.1 | Create High-Level Design | 20 | Kissy Candia | 2025-03-15 | 2025-03-17 | 2025-03-15 | 2025-03-17 | Done
|  | 3.2 | Design Review | 4 | Francis Lloyd Catog | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | Pending
|  | 3.3 | Create Detailed Design | 40 | Bjorn Dimsey Gofredo | 2025-03-19 | 2025-03-21 | 2025-03-19 | 2025-03-21 | Not Started
|  | 3.4 | Finalize Design | 8 | Kissy Candia | 2025-03-22 | 2025-03-22 | 2025-03-22 | 2025-03-22 | Not Started
4 | Implementation |  |  |  |  | 2025-03-23 | 2025-04-03 | 2025-03-23 | 2025-04-03
|  | 4.1 | Phase 1 Implementation | 80 | Team A | 2025-04-04 | 2025-04-10 | 2025-04-04 | 2025-04-10 | Not Started
|  | 4.2 | Phase 2 Implementation | 80 | Team A | 2025-04-11 | 2025-04-12 | 2025-04-11 | 2025-04-12 | Not Started
|  | 4.3 | Implementation Review | 8 | Team A | 2025-04-13 | 2025-04-22 | 2025-04-13 | 2025-04-22 | Not Started
5 | Testing |  |  |  |  | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-14
|  | 5.1 | Create Test Cases | 16 | Kissy Candia | 2025-04-15 | 2025-04-18 | 2025-04-15 | 2025-04-18 | Not Started
|  | 5.2 | Execute Test Cases | 24 | Francis Lloyd Catog | 2025-04-19 | 2025-04-22 | 2025-04-19 | 2025-04-22 | Not Started
|  | 5.3 | Bug Fixes | 16 | Bjorn Dimsey Gofredo | 2025-04-23 | 2025-04-28 | 2025-04-23 | 2025-04-28 | Not Started
6 | Deployment |  |  |  |  | 2025-04-11 | 2025-04-17 | 2025-04-11 | 2025-04-17
|  | 6.1 | Create Deployment Plan | 8 | Team A | 2025-04-12 | 2025-04-18 | 2025-04-12 | 2025-04-18 | Not Started
|  | 6.2 | Deployment | 16 | Team A | 2025-04-13 | 2025-04-19 | 2025-04-13 | 2025-04-19 | Not Started
|  | 6.3 | Post-Deployment Review | 8 | Team A | 2025-04-14 | 2025-04-20 | 2025-04-14 | 2025-04-20 | Not Started
7 | Project Closure |  |  |  |  | 2025-04-15 | 2025-04-21 | 2025-04-15 | 2025-04-21
|  | 7.1 | Document Lessons Learned | 8 | Kissy Candia | 2025-05-01 | 2025-05-02 | 2025-05-01 | 2025-05-02 | Not Started
|  | 7.2 | Final Project Report | 16 | Francis Lloyd Catog | 2025-05-02 | 2025-05-03 | 2025-05-02 | 2025-05-03 | Not Started

## Sheet1
Project X: Automated Attendance System - Traceability
Deadline: May 02, 2025 | [8 empty] | Start Date : March 04, 2025
Requirement ID | Requirements Description | Count | 0 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7 | Task 8 | Task 9 | Task 10
RQ-01 | Gather Requirements |  | x
RQ-02 | Document Requirements |  | x
RQ-03 | Requirement Review |  | x
RQ-04 | Create High-Level Design
RQ-05 | Design Review
RQ-06 | Develop Software
RQ-07 | Test Implementation
RQ-08 | Deployment Preparation
RQ-09 | Post-Deployment Review

## Traceability
TRACEABILITY MATRIX
Act End Date | Sub Task |  | 2025-03-01 |  | End Date | Plan End | 2025-05-02
2025-06-08
Task | Desc | Est Time Days | Plan Start | Actual Start Date
Requirements Capture
R3
TRACEABILITY MATRIX
RO11.01
R01.02
Hello World
Chosen Archeticture
Frontend Setup
Backend Setup
Database Setup
Learn Postman
Testing
Bug Fixing
Standup Practice
Presentation
Client Testing
Security Testing
Multi Platform Testing
UAT [unit testing]
Quality Assurance Testing
Generate & Test 5 QR Codes