## Project Plan
Project X: Automated Attendance System - Project Plan
Deadline: May 02, 2025 | [7 empty] | Start Date : March 04, 2025
Task ID | Task Name | Subtask ID | Subtask Name | Estimated Hours | Assigned To | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Comments
1 | Project Initiation |  |  |  |  | 2025-03-01 | 2025-03-07 | 2025-03-01 | 2025-03-07
|  | 1.1 | Define Project Scope | 4 hours | Kissy Candia | 2025-03-01 | 2025-03-02 | 2025-03-01 | 2025-03-02 | Done
|  | 1.2 | Identify Stakeholders | 4 hours | Francis Lloyd Catog | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | Done
|  | 1.3 | Create Project Charter | 12 hours | Bjorn Dimsey Gofredo | 2025-03-04 | 2025-03-05 | 2025-03-04 | 2025-03-05 | Done
|  | 1.4 | Kickoff Meeting | 2 hours | Team A | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | Done
|  | 1.5 | Finalize Project Plan | 8 hours | Kissy Candia | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | Done
2 | Requirements Analysis |  |  |  |  | 2025-03-08 | 2025-03-14 | 2025-03-08 | 2025-03-14
|  | 2.1 | Gather Requirements | 16 | Team A | 2025-03-08 | 2025-03-10 | 2025-03-08 | 2025-03-10 | Done
|  | 2.2 | Document Requirements | 12 | Kissy Candia | 2025-03-11 | 2025-03-12 | 2025-03-11 | 2025-03-12 | Done
|  | 2.3 | Requirements Review | 8 | Bjorn Dimsey Gofredo | 2025-03-13 | 2025-03-14 | 2025-03-13 | 2025-03-14 | Done
3 | Design Phase |  |  |  |  | 2025-03-15 | 2025-03-22 | 2025-03-15 | 2025-03-22
|  | 3.1 | Create High-Level Design | 20 | Kissy Candia | 2025-03-15 | 2025-03-17 | 2025-03-15 | 2025-03-17 | Done
|  | 3.2 | Design Review | 4 | Francis Lloyd Catog | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | Done
|  | 3.3 | Create Detailed Design | 40 | Bjorn Dimsey Gofredo | 2025-03-19 | 2025-03-21 | 2025-03-19 | 2025-03-21 | Done
|  | 3.4 | Finalize Design | 8 | Kissy Candia | 2025-03-22 | 2025-03-22 | 2025-03-22 | 2025-03-22 | Done
4 | Implementation |  |  |  |  | 2025-03-23 | 2025-04-03 | 2025-03-23 | 2025-04-03 | Done
|  | 4.1 | Phase 1 Implementation | 80 | Team A | 2025-04-04 | 2025-04-10 | 2025-04-04 | 2025-04-10 | Done
|  | 4.2 | Phase 2 Implementation | 80 | Team A | 2025-04-11 | 2025-04-12 | 2025-04-11 | 2025-04-12 | Done
|  | 4.3 | Implementation Review | 8 | Team A | 2025-04-13 | 2025-04-22 | 2025-04-13 | 2025-04-22 | Done
5 | Testing |  |  |  |  | 2025-04-13 | 2025-04-14 | 2025-04-13 | 2025-04-14
|  | 5.1 | Create Test Cases | 16 | Kissy Candia | 2025-04-15 | 2025-04-18 | 2025-04-15 | 2025-04-18 | Done
|  | 5.2 | Execute Test Cases | 24 | Francis Lloyd Catog | 2025-04-19 | 2025-04-22 | 2025-04-19 | 2025-04-22 | Done
|  | 5.3 | Bug Fixes | 16 | Bjorn Dimsey Gofredo | 2025-04-23 | 2025-04-28 | 2025-04-23 | 2025-04-28 | Done
6 | Deployment |  |  |  |  | 2025-04-11 | 2025-04-17 | 2025-04-11 | 2025-04-17
|  | 6.1 | Create Deployment Plan | 8 | Team A | 2025-04-12 | 2025-04-18 | 2025-04-12 | 2025-04-18 | Done
|  | 6.2 | Deployment | 16 | Team A | 2025-04-13 | 2025-04-19 | 2025-04-13 | 2025-04-19 | Done
|  | 6.3 | Post-Deployment Review | 8 | Team A | 2025-04-14 | 2025-04-20 | 2025-04-14 | 2025-04-20 | Done
7 | Project Closure |  |  |  |  | 2025-04-15 | 2025-04-21 | 2025-04-15 | 2025-04-21
|  | 7.1 | Document Lessons Learned | 8 | Kissy Candia | 2025-05-01 | 2025-05-02 | 2025-05-01 | 2025-05-02 | Done
|  | 7.2 | Final Project Report | 16 | Francis Lloyd Catog | 2025-05-02 | 2025-05-03 | 2025-05-02 | 2025-05-03 | Done

## Traceability
TRACEABILITY MATRIX
Act End Date | Sub Task |  | 2025-03-01 |  | End Date | Plan End | 2025-05-02
2025-06-08
Task | Desc | Est Time Days | Plan Start | Actual Start Date
Requirements Capture
R3
TRACEABILITY MATRIX
RO11.01
R01.02
Hello World
Chosen Archeticture
Frontend Setup
Backend Setup
Database Setup
Learn Postman
Testing
Bug Fixing
Standup Practice
Presentation
Client Testing
Security Testing
Multi Platform Testing
UAT [unit testing]
Quality Assurance Testing
Generate & Test 5 QR Codes

## Traceability
Project X: Automated Attendance System - Traceability
Deadline: May 02, 2025 | [8 empty] | Start Date : March 04, 2025
Requirement ID | Requirements Description | Count | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7 | Task 8 | Task 9 | Task 10
RQ-01 | Gather Requirements | 1 | x
RQ-02 | Document Requirements | 1 |  | x
RQ-03 | Requirement Review | 1 |  |  | x
RQ-04 | Create High-Level Design | 1 |  |  |  | x
RQ-05 | Design Review | 1 |  |  |  |  | x
RQ-06 | Develop Software | 1 | [5 empty] | x
RQ-07 | Test Implementation | 1 | [6 empty] | x
RQ-08 | Deployment Preparation | 1 | [7 empty] | x
RQ-09 | Post-Deployment Review | 2 | [8 empty] | x | x